Development Area: Athlete Recruitment and Development

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Provide coaching opportunities for all athletes of all abilities | a. Ensure that a Coaching Structure is in place for all members b. Review Club induction sessions for new members c. Create links for athletes with a Disability so they can participate and improve in athletics | a. Lead Coach b. Lead Coach/ Membership Secretary c. Development Officers | a. Complete b. 2020/21 c. 2021/22 | a/b. N/A c. To explore grass roots funding opportunities |
| 2. Ensure coaching and competition pathway operates effectively | Clear athlete and coaching pathway available for all members to help them achieve their goals | All coaches | Complete | N/A |
| 3. Support developing athletes into regional and national level events should they join Quakers Running Club | Create package for athletes – including any assistance with travel to events | Management Committee | 2021/22 | Cost to be identified from development budget |

Development Area:  Coach and Officials Development

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Increase the number of coaches and officials actively involved in the Club | a. Signpost interested coaches and officials to Education Opportunities b. Develop a volunteer recruitment plan that will target younger coaches and 50 plus to help coach/lead at Club Nights on a rotation c. Identify funding to support coaches and officials to gain qualifications | a. Lead Coach b. Lead Coach/ Development Officers | a. Ongoing b. 20/21 | a/b. Cost to be identified from coaching budget |
| 2. Support coaches and officials in the Club to develop their experience and knowledge | a. Signpost coaches to education opportunities locally, regionally and nationally b. Introduce an informal mentoring programme where experienced coaches can support newer coaches c. Identify funding to support coaches and officials to access further education | a. Lead Coach b. Lead Coach c. Development Officers | a. Ongoing b. Completed c. 2021/22 | a. Costs to be identified from coaching budget b. N/A c. grass roots funding options to be explored |
| 3. Enhance the coaching structure in the Club (see athlete recruitment and development above) | a. Continue the regular coaching meetings and ensure all coaches who cannot attend are communicated with b. Place the Clubs coaching structure on our website (with contacts) c. Ensure the Club has job descriptions for all coaching roles, adapted from UKA | a. Lead Coach/ all coaches b. Coaching assistant/ Web administrator c. Development Officers | a. Monthly b. Completed c. Ongoing | N/A |

Development Area:  Volunteer Recruitment and Development

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Provide outline role descriptions so volunteers understand their role | a. Decide on roles that require to be fulfilled by Club b. Outline roles (adapted from UKA) c. Communicate this with members | a/b/c. Management Committee | - Completed - March 2020 - March 2020 | N/A |
| 2. Create a system for recruiting, retaining and recognising volunteers within the Quakers Running Club structure | a. Recruit volunteers at club events/activities b. Have a bi – annual activity evening for volunteers c. Each year, at Annual Club Awards evening, have awards for club volunteers. | a/b/c. Management Committee | a. Ongoing b. Twice per year – near Christmas and Summer c. Annually | Costs to be identified from development budget |

Development Area:  Training and Competition

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Provide competition at all Levels | a. Ensure we have Team Managers for each competition b. Ensure coaches, athletes are aware of competition pathway and how each competition operates c. Ensure we have coaches in place to support the preparation for these matches (links to Coaches Meetings – see above) | a. Management Committee b. Team Captains (Road, Track, Fell, X-Country) c. Lead Coach | a/b/c. Completed | N/A |
| 2. Create a fixture list appropriate for our Club Athletes | Signpost members especially new and young members to competition opportunities locally, regionally and nationally and provide a support structure | Team Captains/ Newsletter Officers | Completed | N/A |
| 3. Continue to organise the QRC Lyke Wake Race | a. Annually establish a sub-group with support from local council and other bodies when appropriate (police, scouts, companies) b. Follow the race Action Plan c. Ensure budgets are in place | a/b/c. Race Development Committee | Ongoing | All costs to be managed within the Lyke Wake budget |

Development Area:  Partners (Develop Community to Club Links)

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Link Club officially to social running groups within Darlington | a. Create clear pathway for members b. Put in place membership options for different group | - Development Officers - Treasurer | 2020/21 | N/A |
| 2. Introduce formal Come and Try Days through local GPs, social running groups, health funded initiatives | Invite interested parties to organised coaching sessions and ensure this is part of the club’s ongoing work | Secretary/ Development Officers | 2020/21 | TBC |
| 3. Work in partnership with key agencies | a. Regularly attend and participate in Local Athletics Partnership b. Link with Sports Development Team and Regional Manager for England Athletics to help to execute this Development Plan | a/b. Management Committee | 2020/21 | N/A |

Development Area: Management (Administration, Welfare, Finance, Facilities/Equipment, Marketing)

| Objectives What are we trying to achieve? | Actions How are we going to achieve it? | Personnel Who is going to do it? | Completion date | What will it cost? |
| --- | --- | --- | --- | --- |
| 1. Improve the effectiveness of the Club Management Structure | a. Use this Development Plan as key driver for Club Management and Development b. Review the structure of the Club and identify any key gaps or change required c. Organise annual seminar/planning day for the Club to ensure full club support | a/b/c. Chair and Management Committee | AGM 2020 | N/A |
| 2. Maintain and Develop facilities for Clubs | a. Sub-group formed to work with Local Authority to develop and maintain facilities for athletics in the area b. Continue to work to find the best site for Quakers Running Club train and to develop the offer | a/b/c. Chair and Management Committee | 2020/21 | TBC |
| 3. Ensure robust Welfare/Child Protection procedures are in place | a. Ensure Club Welfare Officer has attended relevant training b. Ensure all Club Coaches complete the necessary online safeguarding course c. Ensure the Club’s Welfare Policy and contacts are on the website d. Ensure all members who are undertaking regulated work have relevant Disclosure Checks in place | a-d. Club Welfare Officer with support from Club Committee | - In progress - Ongoing - In progress - Completed - ongoing | Safeguarding course cost reimbursed from coaching budget |
| 4. Develop Club Financial procedures and structures so we can fulfil our Development Plan | a. Identify grants and sponsorship opportunities b. Work with key partners including England Athletics, Local Councils etc to tap into any relevant funding that is available c. Support athletes who are at National/International Level – establish criteria and funding model | a-c. Management Committee | a-c. 2020/21 | TBC |
| 5. Create marketing materials and opportunities for the Club. | a. Produce promotional material for community links (see partnership working) b. Set up Club facebook page c. Develop the Club webpage by adding further sections and recruiting key volunteers to maintain and regularly update the site d. Produce standard member welcome email with all key club details | a. Development Officers b/c. Web Administrator d. Membership Secretary | - 2020/21 - Completed - Completed – ongoing - In progress |  |